# Change Request Form

| Change Request ID | CR-01 |
| --- | --- |
| Change Date | 16th October 2014 |
| Project Name | HanDIYcraft |
| Document Name | Project Plan |
| Document Version | Version 1.2 |
| Team Member | Ms. Nahathai Kaewtatib |
|  | Ms. Pimchanok Sripraphan |

| Change Detail |  |  |  |  |
| --- | --- | --- | --- | --- |
| Change type | □ Change | □ Add | □ Remove | ☑ Postpone |
| Specify Location | - Feature 3: Shop Management (only the part of web application), consists of three functions as following: - Search shop name by keyword. - Display shops that exist in the database randomly. - Display shop's detail, which contain shop name, shop owner username, branch, telephone number, information, shop's pictures, and location. - Feature 4: Map Management (on both web and mobile application), consists of three functions as following: - See the shop's location via Google Maps. (On both web and mobile) - See shops’ location near by the user via Google Maps. (On mobile) - Pin shop's location via Google Maps by shopkeeper. (On mobile) |  |  |  |
| Change Reason | At first, we planned to develop the feature 3: shop management only on mobile application. However, since we have discussed more about it in the previous progress, we were asked to develop this feature on web application too. The functions of this feature that will be developed are shop exploration and seeing shop detail. Moreover, in this progress we have re-arranged the graphic user interface on both systems too. Due to those reasons, they effected on our time management, we are unable to complete them on time. Therefore we decided to shift those features to be developed in the next progress. |  |  |  |

Change Effect

Due to there are two features shifted to the next progress, and there is only one feature, which is feature 6: Notification Management left. Therefore, time management in the next progress will be changed. However, those features are not too complicated to implement because they are quite similar to the feature 2: Tutorial Management, which is already completed in the previous progress. To prevent the delay problem, we tend to reduce time consuming of each feature in the project plan. Since the time duration in the next progress is 17 days (2/11/2014-19/11/2014) This is what we have planned for implementing other three features. - Feature 3: Shop Management (only on web application) 2/11/2014 – 6/11/2014 (5 days) - Feature 4: Map Management (on both web and mobile application) 7/11/2014-13/11/2014 (7 days) - Feature 6: Notification Management (on both web and mobile application) 14/11/2014-16/11/2014 (3 days)

| Request Approve |  |  |
| --- | --- | --- |
|  | Name | Signature |
| Request Person | Ms. Nahathai Kaewtatib |  |
| Review Person | Ms. Pimchanok Sripraphan |  |
| Approve Person | Ms. Siraprapa Wattanakul |  |