# Change Request Form

| Change Request ID | CR-01 |
| --- | --- |
| Change Date | 16th October 2014 |
| Project Name | HanDIYcraft |
| Document Name | Project Plan |
| Document Version | Version 1.2 |
| Team Member | Ms. Nahathai Kaewtatib |
|  | Ms. Pimchanok Sripraphan |

| Change Detail |  |  |  |  |
| --- | --- | --- | --- | --- |
| Change type | □ Change | □ Add | □ Remove | ☑ Postpone |
| Specify Location | - Feature 3: Shop Management (only the part of web application), consists of three functions as following: - Search shop name by keyword. - Display shops that exist in the database randomly. - Display shop's detail, which contain shop name, shop owner username, branch, telephone number, information, shop's pictures, and location. - Feature 4: Map Management (on both web and mobile application), consists of three functions as following: - See the shop's location via Google Maps. (On both web and mobile) - See shops’ location near by the user via Google Maps. (On mobile) - Pin shop's location via Google Maps by shopkeeper. (On mobile) |  |  |  |
| Change Reason | At first, we planned to develop the feature 3: shop management only on mobile application. However, since we have discussed more about it in the previous progress, we were asked to develop this feature on web application too. The functions of this feature that will be developed are shop exploration and seeing shop detail. Moreover, in this progress we have re-arranged the graphic user interface on both systems too. Due to those reasons, they effected on our time management, we are unable to complete them on time. Therefore we decided to shift those features to be developed in the next progress. |  |  |  |

Change Effect

Due to there are two features shifted to the next progress, and there is only one feature, which is feature 6: Notification Management left. Therefore, time management in the next progress will be changed. However, those features are not too complicated to implement because they are quite similar to the feature 2: Tutorial Management, which is already completed in the previous progress. To prevent the delay problem, we tend to reduce time consuming of each feature in the project plan. Since the time duration in the next progress is 17 days (2/11/2014-19/11/2014) This is what we have planned for implementing other three features. - Feature 3: Shop Management (only on web application) 2/11/2014 – 6/11/2014 (5 days) - Feature 4: Map Management (on both web and mobile application) 7/11/2014-13/11/2014 (7 days) - Feature 6: Notification Management (on both web and mobile application) 14/11/2014-16/11/2014 (3 days)

| Request Approve |  |  |
| --- | --- | --- |
|  | Name | Signature |
| Request Person | Ms. Nahathai Kaewtatib |  |
| Review Person | Ms. Pimchanok Sripraphan |  |
| Approve Person | Ms. Siraprapa Wattanakul |  |

| Change Request ID | CR-02 |
| --- | --- |
| Change Date | 4th December 2014 |
| Project Name | HanDIYcraft |
| Document Name | Software Requirement Specification |
| Document Version | Version 3.0 |
| Team Member | Ms. Nahathai Kaewtatib |
|  | Ms. Pimchanok Sripraphan |

| Change Detail |  |  |  |  |
| --- | --- | --- | --- | --- |
| Change type | □ Change | □ Add | ☑ Remove | □ Postpone |
| Specify Location | Remove some functions on web application since those functions are already exist on mobile application as following: - Blogger will not be able to explore and search shops’ information, which includes location of shops on the website. - Blogger will not be able to use communication functions, e.g. comment, message, like, follow, and share tutorial on Facebook. - Therefore, there will not be notification function when there is new tutorial comment, tutorial like, or follower. |  |  |  |
| Change Reason | At first, we planned to develop our system only on mobile application. However, since we have discussed more about it in the first progress, we were asked to develop several features on web application too. The features on web application are authorization, tutorial, shop, map, communication, and notification management. Moreover, in this progress we have re-arranged the graphic user interface on both systems and combine all the features together to make the system looks perfect as much as possible. Due to those reasons, they effected on our time management. We are unable to complete everything on time. Therefore, we decided to cut shop, map, communication, and notification management out from web application. Hence, only authorization and tutorial management are there on web application. |  |  |  |

Change Effect

Due to only authorization and tutorial management will be there on web application, the user may have to use the rest features of the system on mobile application.

| Request Approve |  |  |
| --- | --- | --- |
|  | Name | Signature |
| Request Person | Ms. Nahathai Kaewtatib |  |
| Review Person | Ms. Pimchanok Sripraphan |  |
| Approve Person | Ms. Siraprapa Wattanakul |  |